## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | Backlog Item/User Story | Tasks | Owner | Status | Estimated effort (hours) | Actual Effort (hours) | AI Involvement | What was the AI task(s)? - more than one option can be selected
[8 empty] | Explain | Suggest | Create | Change | Check | Other? (explain in text)
US1 | As a SOC analyst, I want to submit an incident case containing Elastic/Wazuh security alerts so that the AI analyst can start investigating the observed activity. | Define the supported Elastic/Wazuh incident case JSON structure. | Ethan | DONE | 4
|  | Define mandatory fields and case validation rules. | Ethan | DONE | 3
|  | Create simulated valid and invalid incident case samples. | Ethan / Isabela | DONE | 4
|  | Implement the incident case parser and validator. | Isabela | DONE | 5
|  | Implement the backend endpoint for incident case submission. | Santiago | DONE | 5
|  | Generate and assign a unique identifier to accepted cases. | Santiago | DONE | 2
|  | Implement automated tests for valid and invalid case submissions. | Roberto | DONE | 4
US2 | As a SOC analyst, I want the agent to identify relationships between alerts and events within a case so that I can distinguish related attack activity from unrelated or noisy events. | Define the evidence that can indicate relationships between events (IP, host, user, timestamp, process, IoC, etc.). | Ethan | DONE | 4
|  | Define the internal representation of relationships and supporting evidence. | Francisco | DONE | 4
|  | Define how uncertain, related and unrelated events will be represented. | Ethan / Francisco | DONE | 3
|  | Implement an initial alert/event correlation mechanism. | Francisco | DONE | 8
|  | Implement handling of unrelated and uncertain alerts. | Francisco | DONE | 4
|  | Create test cases containing related events and unrelated noise. | Isabela | DONE | 3
|  | Test and document correlation results against expected relationships. | Roberto / Ethan | DONE | 4
US3 | As a SOC analyst, I want the agent to use pre-enriched IoC information so that existing threat intelligence can support the investigation without repeating enrichment. | Define the expected pre-enriched IoC input structure based on N8N output. | Ethan | IN PROGRESS | 3
|  | Implement parsing and validation of pre-enriched IoC information. | Santiago | DONE | 4
|  | Add IoC enrichment data to the internal investigation context. | Francisco / Santiago | DONE | 4
|  | Verify that findings can reference IoC enrichment information as supporting evidence. | Ethan / Francisco | DONE | 3
|  | Implement tests for cases with and without enrichment information. | Isabela | DONE | 3
[5 empty] | 74 | 0

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG
ID | Backlog Item/User Story | Tasks | Owner | Status | Estimated effort (hours) | Actual Effort (hours) | AI Involvement | What was the AI task(s)? - more than one option can be selected
[8 empty] | Explain | Suggest | Create | Change | Check | Other? (explain in text)

## AI Labels
Label | Meaning | Label | Meaning
H | No generative AI was used for this task. | Explain | AI provided information or helped us understand something (e.g., what does Error 501 mean?).
H+AI | Both human and generative AI materially contribute | Suggest | AI proposed ideas, options, plans, or possible solution(s).
AI | Substantive artifact generated primarily by AI; humans prompt and minimally edit. | Create | AI produced new code, text, designs, or other work used in the task.
|  | Change | AI modified, improved, refactored, or corrected existing work.
|  | Check | AI reviewed, tested, critiqued, or evaluated work.